# Application for support

General

Project name: Pre-study for capasity building a network of cooperation in the field of Finno Ugric cultures, languages and sustainable tourism in the North

Application id: 446254

Case id:

Application call: 4.1 Cross-border capacity building

Responsible organisation: Interreg Aurora

Lead partner EU

| Name: Runolaulu-Akatemian kannatusyhdistys ry | Org. No: 2660747-6 |
| --- | --- |
| Kainuuntie 99 88900 Kuhmo Finland | Employees: 3 |
| Workplace |  |
| Name: Runosong Academy | Workplace No.: 1 |
| Postal address: | Visitors address: |
|  | Region: Kuhmo |

Lead partner motivation and contribution

Runosong Academy is independent national cultural and research centre, supported by its own association (Runosong Academy Support association). It is operating internationally in cooperation with other research and cultural institutes. Runosong Academy is specialised on runosong and other singing and music traditions research, artistic and pedagogic activities. In addition to that, some of the most important priorities of the Runosong Academy are intangible cultural heritage and sustainable cultural tourism.

Runosong Academy is the coordinator and key operator for Kuhmo as Finno-Ugric Cultural Capital 2023. This preparatory project aims to build up a network capable of applying a regular project in 2024, to keep the cooperation network alive, viden and strenghten it in coming years. The contacts in the Northern areas of Finland, Sweden and Norway have become most important in resent years.

Is your organisation entitled to recover VAT based on national

legislation for the activities implemented in the project?

No

Name of legal representative

Pekka Huttu-Hiltunen

Project partner EU

| Name: Meänsuomen Föreeninki - Byfinska Föreningen | Org. No: 802467-8859 |
| --- | --- |
|  | Employees: 0 |
| Postal address: |  |
| Rapsodivägen 48 |  |
| 14241 SKOGÅS |  |
| Sverige |  |

Workplace

| Name: | Workplace no: |
| --- | --- |
| Postal address: | Visitors address: |
|  | Region: |

Partner motivation and contribution

Meansuomen Föreeninki - Byfinska Föreningen has its focus and operations directed to the georgaphical area of Norbotten. "An exception can be made for organisations based outside the programme area but having the responsibility for the whole nation regarding specific issues."

We are interested in supporting Meänkieli in the North, and also cultural exhange and sustainable cultural tourism in the Northern areas of Finland, Sweden and Norway. In future, we aim to seek also other partners in Norbotten for the the nexcty stage, in the regular project in 2024.

Is your organisation entitled to recover VAT based on national

legislation for the activities implemented in the project?

No

Name of legal representative

Birger Winsa

| Name: University of Oulu | Org. No: 0245895-5 |
| --- | --- |
|  | Employees: 3000 |
| Postal address: |  |
| Pentti Kaiteran katu 1, Linnanmaa |  |
| 90014 Oulun yliopisto |  |
| Finland |  |

Workplace

| Name: Humanistinen tiedekunta | Workplace no: 16 |
| --- | --- |
| Postal address: | Visitors address: |
| PL 1000 | Linnanmaa, Erkki Koiso-Kanttilan katu 1, 3. krs |
| 90014 Oulun yliopisto | 90014 Oulu |
|  | Region: Uleåborg |

Partner motivation and contribution

The unit of Oulu university is The Giellagas Institute for Saami Studies. We are interested in joining the cooperation network and especially in developing research and cultural studies in the coming years. We want to organise reserch conference in 2024, which are handling Sámi music, dance and oral history. In future we want to be in cooperation with also other activities.

The seminar in 2024, which is in our goals for the network, would be co-organized by the Oulu Culture Foundation as a part of the Sámi program of the region's year as the European Capital of Culture, Oulu2026.

Is your organisation entitled to recover VAT based on national

legislation for the activities implemented in the project?

Partly

VAT-number (Optional)

FI02458955

Name of legal representative

Anni-Siiri Länsman

Lead partner Norway

| Name: Kvensk Finsk Riksforbund | Org. No: 991939180 |
| --- | --- |
| c/o Bjørnar Seppola Gammelveien 70 9143 Skibotn Norge | Employees: 1 |
| Workplace |  |
| Name: Skibotn | Workplace No.: 18181818 |
| Postal address: c/o Bjørnar Seppola Gammelveien 70 9143 Skibotn | Visitors address: c/o Bjørnar Seppola Gammelveien 70 9143 Skitbotn |
|  | Region: Troms og Finnmark |

Lead partner motivation and contribution

We would like to have cooperation with Runsong Academy in Kuhmo, also the Giellagas Institute in Oulu University and Meänkieli Färeeninki in Sweden, when thinking about our cultural, language and tourism developmen in future. This small scale project is to begin the development and at the same time prepare a regular project in these themes for the year 2024. Runosong Academy has lots of experience in transnational cooperation, and thas why we are interested also to learn cooperation methods with them.

Is your organisation entitled to recover VAT based on national

legislation for the activities implemented in the project?

No

Name of legal representative

Bjørnar Seppola

Project partner Norway

Payment information

Type of payment method: BIC/IBAN

Account number: OKOYFIHH FI89 5177 0020 0910 68

Project information

### Project title

Capasity building a network of cooperation in the field of Finno Ugric cultures, languages and sustainable tourism in the North (Pro Ntw FU)

### Project type

Small-scale project

### Project start date

6/25/23

### Project end date

12/30/23

### Programme sub-area

Aurora

### What are the common territorial challenge(s) that will be tackled by the project?

Kuhmo was chosen as Finno-Ugric Cultural Capital in 2023. It was the first time this nomination was appointed to Finland. Shortly after the international jury decision (in January 2022) Russia attacked Ukraine, and many of the ideas of the CC-year in Kuhmo had to be changed, because Russia cannot be part of the year. Quite shortly it was realised, that now is the momentum to reinforce the Nordic cooperation, and also build new network for cultural tourism.

Now, during the FUCC-year, and especially after that, is the right time to build a network of Kvens in Norway, Forest Finns in Sweden and Norway, Meänkieli-area in Sweden, Saami areas in Finland, Sweden and Norway with Finns. This network would focus on languages and cultural issues, also research, and it would also - in the future - enhance sustainable cultural tourism. FUCC-year is a good starting point for these operations.

The idea is transnational for the beginning. Target groups in the long run are for the first, language and cultural experts, activists and institutions in all participating countries, secondly cultural tourism operators and business, and thirdly large audience.  We want people to appreciate the cultural diversity in the North. Runosong Academy has had contacts with many experts in linguistics as well as ethnomusicologists in Nordic countries.

This small scale project is primatrily for buiding sitable and well-balanced sross-border partnerships in the Nothern areas. After this stage, in the beginning of 2024 we aim to start a regular project, maybe with some additional partners, in order to get sustainable results for the origilan idea (descibed above).

This project has no direct predecessors, but Runosong Academy has had many (more than 20 during the 1998-2022) EU and other projects which make contacts in Finland, in Nordic states, with Russian Karelia and the Baltic states. (Also Bretagne, Scotland). Most of these projects have linguistic and cultural programs.

### Why is cross-border cooperation needed to achieve project objectives and results?

This small scale project is to build and stregthen the network, first, and get real process started in planning of a regular project in coming months.

The idea is transnational for the beginning. Thats why it is only possible by cross border network and activities. Target groups for the cooperation in future are for the first, language and cultural experts and activists in all participating countries, secondly cultural tourism operators and business, and thirdly large audience. Ultimately we want the large audience to notice that there are also many Finno-Ugric languages spoken in the Nordic countries, and that they have distinctive, sometimes unique cultural features in their social existence. We want people to appreciate the cultural diversity in the North.

### Select the project's main target group

Civil society

### Specification of the target group and their involvement in project planning

Target groups are for the first, cultural organisations and activists and institutes, later and secondly also language and cultural experts and  and also tourism organisations in all participating countries, and thirdly large audience. We want the large audience to notice that there are also many Finno-Ugric languages spoken in the Nordic countries, and that they have distinctive, sometimes unique cultural features in their social existence. We want people to appreciate the cultural diversity in the North.

Runosong Academy has had contacts with many experts in linguistics as well as ethnomusicologists in Nordic countries. Also, the contacts with cultural tourism are familiar from the previous projects. For instance RA is active partner in the Singing heritage Association, which is applying certification as European Cultural Route for the SH-Route from the Council of Europe.

Runosong Academy has also developed Ontrei Malinen's Kantele Route, which is now managed by the Via Karelia, the oldest official cultural route in Finland. So, boths target groups are familiar from the previous activities.

### Which synergies with past or current EU and other projects, initiatives, strategies and/or policies will the project make use of?

This project has no direct predecessors, but Runosong Academy has had many (more than 20 during the 1998-2022) EU and other projects which make contacts in Finland, in Nordic states, with Russian Karelia and the Baltic states. (Also Bretagne, Scotland). Most of these projects have linguistic and cultural programs.

One interestin dimension is the Runosong Academy is the key operator in Singing Heritage Route -initiative, which has been given in 2022 to the European Council. Maybe in the future the Route could continue also to the areas of Sámi and Kven cultures in the North. Anyway, sustainable cultural tourism development is important sector in the project idea.

### Project overall objective

The small scale project is to build suitable and well-balanced cross-border partnerships and network in the areas of Eastern Finland and Northern areas of Sweden and Norway. Within the preliminary project we stregthen the cooperation with these four partners, hopefully also get some suitable additional partners for the next step, and prepare pland for sustainable cultural and tourism developlent between the areas.

The purpose of the overall project idea is to increase also cohesion in the Finno-Ugric language and culture areas which exist in the Nordic countries, to recognize and preserve their own linguistic identity and to open up connections to the rest of the Finno-Ugric world.

At the same, our objective is that the rest of wide audiencein the Nordic countries get information about the language minorities and their cultures found in the Nordic countries.

The goal is also to increase cultural tourism in the area, and create cooperation network in the South-North direction.

### Ecological sustainable development

The project does not directly operate on ecological questions. However, succesful implementation of the project and especially the future cooperation is dependent on sustainable development on environment. Nature has to be kept as it is, and new protected areas have to be established, to keep the areas attractive for local people as well as visiting tourists.

### Social sustainable development

Sustainable cultural tourism means that activities have to be socially and culturally sustainable. Local way of life, the values of the people have to be respected. Cultural identity and behaviour has to be respected, and the income of activities have to benefit local people. This leads into social concession. Also, cultural heritage is carefully taken into consideration, so that the elements are respected, andt they can survive even stronger after sustainable activities.

### Economical sustainable development

The benefits of project activities have to finally go mostly to the local enterprises and people. This is our goal. One has to notice that all organisations and people connected to them are local. They live in the area and work for the area.

### Exit strategy

The cooperation network is created to last and even strengthen after the project. Organisations and their activities will continue, and new solutios will be developed. Both cultural and tourism aspects are important. For instance, the Singing Heritage Route is aimed to continue even further to the North in future. Also, festival cooperation will continue, and the project gives new perspectives to all partners and co-partners.

### Project summary

The small scale project is to strengthen the network and begin to prepare a regular project for the next year. The whole idea of these projects are:

Capasity building a network of cooperation in the field of Finno Ugric cultures, languages and sustainable tourism in the North (Pro Ntw FU)

The program specific objective of the project is capasity building. The ultomate goal for the network is to increase cohesion in the Finno-Ugric language and culture areas which exist in the Nordic countries, to recognize and preserve their own linguistic identity and to open up connections to the rest of the Finno-Ugric world.

At the same, our objective in the next stage is that the rest of wide audience in Nordic countries get information about the language minorities and their cultures found in The Nordic countries. The goal is also to increase cultural tourism in the area, and create cooperation network in the South-North direction.

On the background of the project is, that Kuhmo is nominated as the Finno-Ugric Cultural Capital 2023. This is the first time when this nomination is given to Finland. At the same, Russias attack to Ukraine has dramatically prevented many Finno-Ugric groups to participate the program. Now, there is the right momentum to strengthen contacts in Nordic countries, Saami, Kven, Meänkieli and Forest Finns areas, as well as to Estonian and Hungarian cultures.

The opening event of the FUCC 2023 year was in February, and all partners visited it. During the same week. there was an international conference dealing the situation of Finno-Ugric languages, especially of those of indigenous peoples. The idea is to continue this cooepration and widen it. The next steps will be taken after this project.

### How will the project partnership be structured?

The small scale project is to strengthen the network and confirm understanding of the demands of the overall project idea.

The project entity shall be designed jointly, so that all partners are fully aware of their chare and responsibility of the plan.

All questions are handled also afterwards and reflected to the objectives of the project. This makes it possible to react, if something doesn't seem to go into right direction.

Financial information is collected by the Lead Partner. The Lead Partner has responsibility of all.

### How will the financial management of the project be handled?

Financial information is collected by the Lead Partner. The Lead Partner has responsibility of all.

In each country, the partners have their own budget. It will be looked regularly to make sure that ell is correct. The Lead Partner will collect the information and combine it to the financial reports, when needed.

### How will you communicate your project?

Communication is one of the most important tasks in the project, and in connection to the main objectives. Thats why there is one work package especially for that.

Project will communicate by regular meetings and email between partners. For the target groups, there will be a news letter published in the end of the project.

The project will produce a website in connection of Runosong Academy website. It will be linked to all partners websites. Project will be present in social media, at least Facebook and Instagram.

Project activities

| Workpackages / Activities | Description | Start date – End date | Cost |
| --- | --- | --- | --- |
| 1 - WP 1: Implementation in Finland | The activities in Finland 2023 are important to plan the future and to strengten the network. | 6/25/23 - 12/30/23 | 4,000 |
| 1.1 - Starting meeting in June-July | 1.1 The starting meeting in 2023 ais important to plan the future. People from partner organizations will come to the meeting in Kuhmo. | - | 2,500 |
| 1.2 - 1.2 Final meeting in Finland in November - December 2023 | In the end of the year 2023, most probably in November, the partners will have another real meeting in Kuhmo. Plans for regular project are made. | - | 1,500 |
| 2 - WP 2: Implemetation in Norway | Activities which are operated by the Norwegian partner | 6/25/23 - 12/30/23 | 3,400 |
| 2.1 - 2.1 Participation in meetings in Finland 2023 | The partners representatives will participate the start meeting in June-July and final meeting in the end of the year 2023. In meanwhile, distant connections are held and meetings and preparing workshops are held. | - | 2,400 |
| 2.2 - 2.2 Creating a cooperation network in Norway | The Norwegian partner is looking for possible new parner in the next stage of cooperation. Also cooperative partners are looked for. | - | 1,000 |
| 3 - WP 3: Implementation is Sweden | The Swedish partner operates in these activities | 6/25/23 - 12/30/23 | 4,600 |
| 3.1 - 2.2: Widening the network in Sweden | The Swedish partner is working for Meänkieli, but has it's address in South of Sweden. That's whay we should find at least one suitable partner located in the Aurora area. Also cooperating partners are looked for. There are most probably meetings and travel costs in Sweden for that purpose. | - | 2,500 |
| 3.2 - 2.2 Participating the meetings in Finland | The partners representatives will participate the start meeting in June-July and final meeting in the end of the year 2023. In meanwhile, distant connections are held and meetings and preparing workshops are held. | - | 2,100 |
| 4 - WP 4: Communication and Dissemination | The project will communicate and disseminate its results | 6/25/23 - 12/30/23 | 2,000 |
| 4.1 - 4.1 Communication and Dissemination | It is important to communicate and disseminate the project activities and results. That is why a web-site is created in connection to Runosong Academy web-site. Later, in the regular project, the web-site will be used to communicate also the regular project. | - | 2,000 |

Indicators

Output indicators

| Solutions for legal or administrative obstacles across border identified | We should have more partners and cooperating partners (not actual partners, but in cooperation with the project) | Startvalue: N/A Targetvalue: 1 Unit: Solutions |
| --- | --- | --- |
| Strategies and action plans jointly developed | Action plan for the regular project and development in cooperation for coming years | Startvalue: N/A Targetvalue: 1 Unit: Joint strategies/action plans |
| Organisations cooperating across borders | We should have more, but 4 in the beginning | Startvalue: N/A Targetvalue: 4 Unit: Organisations |

Result indicators

| Joint strategies and action plans taken up by organisations | Action plane for the future cooperation in the field of culture, language and cultrural tourism | Startvalue: Targetvalue: 1 Unit: Joint strategies/action plans |
| --- | --- | --- |
| Legal or administrative obstacles addressed or alleviated | We will find new partners in the area (also cooperating partners) | Startvalue: Targetvalue: 1 Unit: Legal and administrative obstacles |
| Organisations cooperating across borders after project completion | One more partner in Sweden and one more in Norway - for the future cooperation | Startvalue: Targetvalue: 6 Unit: Organisations |

Budget EU

Costs

| Cost categories | Runolaulu-Akatemian kannatusyhdistys ry | Meänsuomen Föreeninki - Byfinska Föreningen |  | University of Oulu |  |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Staff cost: Project director / coordinator (6 months x 0,15 %) | 4,242 | 4,000 |  | 5,000 |  |  |  |  |  |  |  | 13,242 |
| Staff cost: Project secretary (6 minths x 10 %) | 2,303 | 0 |  | 0 |  |  |  |  |  |  |  | 2,303 |
| Office and administrative costs 15% | 982 | 600 |  | 750 |  |  |  |  |  |  |  | 2,332 |
| Travel and accommodation costs 15% | 982 | 600 |  | 750 |  |  |  |  |  |  |  | 2,332 |
| External expertise and service costs: External experts in the meetings (incl. transport, accommodation etc) | 2,000 | 2,000 |  | 2,000 |  |  |  |  |  |  |  | 6,000 |
| Costs for infrastructure and works: Communication and dissemination | 850 | 100 |  | 100 |  |  |  |  |  |  |  | 1,050 |
| Sum costs | 11,359 | 7,300 |  | 8,600 |  |  |  |  |  |  |  | 27,259 |
| Deduction of project income |  |  |  |  |  |  |  |  |  |  |  |  |
| Total deduction |  |  |  |  |  |  |  |  |  |  |  |  |
| Total costs | 11,359 | 7,300 |  | 8,600 |  |  |  |  |  |  |  | 27,259 |
| Sum total costs | 11,359 | 7,300 |  | 8,600 |  |  |  |  |  |  |  | 27,259 |

Financing

| Financier | Runolaulu-Akatemian kannatusyhdistys ry | Meänsuomen Föreeninki - Byfinska Föreningen | University of Oulu |  |  |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Public co-financing |  |  |  |  |  |  |  |  |  |  |  |  |
| National co-financing (25%): To be applied | 2,840 | 1,825 | 2,150 |  |  |  |  |  |  |  |  | 6,815 |
| Total public co-financing | 2,840 | 1,825 | 2,150 |  |  |  |  |  |  |  |  | 6,815 |
| Total all public co-financing methods | 2,840 | 1,825 | 2,150 |  |  |  |  |  |  |  |  | 6,815 |
| Private co-financing |  |  |  |  |  |  |  |  |  |  |  |  |
| Parters own financing: Partners own financing (can include grants etc.) | 1,136 | 730 | 860 |  |  |  |  |  |  |  |  | 2,726 |
| Total private co-financing | 1,136 | 730 | 860 |  |  |  |  |  |  |  |  | 2,726 |
| Total all private co-financing methods | 1,136 | 730 | 860 |  |  |  |  |  |  |  |  | 2,726 |
| Total public and private co-financing | 3,976 | 2,555 | 3,010 |  |  |  |  |  |  |  |  | 9,541 |

Support

| Financing | Runolaulu-Akatemian kannatusyhdistys ry | Meänsuomen Föreeninki - Byfinska Föreningen | University of Oulu |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total financing | 7,383 | 4,745 | 5,590 |  |  |  |  |  |  | 17,718 |

Support and financing

|  | Runolaulu-Akatemian kannatusyhdistys ry | Meänsuomen Föreeninki - Byfinska Föreningen | University of Oulu |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total financing | 11,359 | 7,300 | 8,600 |  |  |  |  |  |  | 27,259 |

Compilation

|  | Runolaulu-Akatemian kannatusyhdistys ry | Meänsuomen Föreeninki - Byfinska Föreningen | University of Oulu |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sum total costs | 11,359 | 7,300 | 8,600 |  |  |  |  |  |  | 27,259 |
| Sum co-financing | 3,976 | 2,555 | 3,010 |  |  |  |  |  |  | 9,541 |
| Applied support | 7,383 | 4,745 | 5,590 |  |  |  |  |  |  | 17,718 |
| Support share | 65.00% | 65.00% | 65.00% |  |  |  |  |  |  | 65.00% |

| Support share of actual costs | 65.00% |
| --- | --- |
| Support share of total costs | 65.00% |
| Support share of financing base for support | 65.00% |
| Support share of total financing | 65.00% |
| Support share of other public co-financing | 25.00% |
| Support share of public co-financing | 90.00% |
| Support share of private co-financing | 10.00% |

Norwegian budget

Costs

| Cost categories | Kvensk Finsk Riksforbund |  |  |  |  |  |  |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Staff cost: Norwegian coordinator (6 monhs x 25 %) | 7,500 |  |  |  |  |  |  |  |  |  |  |  |  | 7,500 |
| Office and administrative costs 15% | 1,125 |  |  |  |  |  |  |  |  |  |  |  |  | 1,125 |
| Travel and accommodation costs 15% | 1,125 |  |  |  |  |  |  |  |  |  |  |  |  | 1,125 |
| External expertise and service costs: External experts in meetings (potential partners etc.) | 2,000 |  |  |  |  |  |  |  |  |  |  |  |  | 2,000 |
| Costs for infrastructure and works: Communication and Dissemination | 800 |  |  |  |  |  |  |  |  |  |  |  |  | 800 |
| Sum costs | 12,550 |  |  |  |  |  |  |  |  |  |  |  |  | 12,550 |
| Deduction of project income |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total deduction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total costs | 12,550 |  |  |  |  |  |  |  |  |  |  |  |  | 12,550 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
| Sum total costs | 12,550 |  |  |  |  |  |  |  |  |  |  |  |  | 12,550 |

Financing

| Financier | Kvensk Finsk Riksforbund |  |  |  |  |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Public financing |  |  |  |  |  |  |  |  |  |  |  |  |
| National co-financing: National co-financing | 6,275 |  |  |  |  |  |  |  |  |  |  | 6,275 |
| Total public financing | 6,275 |  |  |  |  |  |  |  |  |  |  | 6,275 |
| Total all public financing methods | 6,275 |  |  |  |  |  |  |  |  |  |  | 6,275 |
| Private financing |  |  |  |  |  |  |  |  |  |  |  |  |
| Total private financing |  |  |  |  |  |  |  |  |  |  |  | 0 |
| Total all private financing methods |  |  |  |  |  |  |  |  |  |  |  | 0 |
| Total public and private financing | 6,275 |  |  |  |  |  |  |  |  |  |  | 6,275 |

Support

| Financing | Kvensk Finsk Riksforbund |  |  |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Applied support | 6,275 |  |  |  |  |  |  |  |  | 6,275 |

Support and financing

|  | Kvensk Finsk Riksforbund |  |  |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total financing | 12,550 |  |  |  |  |  |  |  |  | 12,550 |

Compilation

|  | Kvensk Finsk Riksforbund |  |  |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sum total costs | 12,550 |  |  |  |  |  |  |  |  | 12,550 |
| Sum co-financing | 6,275 |  |  |  |  |  |  |  |  | 6,275 |
| Applied support | 6,275 |  |  |  |  |  |  |  |  | 6,275 |
| Support share | 50.00% |  |  |  |  |  |  |  |  | 50.00% |

| Support share of actual costs | 50.00% |
| --- | --- |
| Support share of total costs | 50.00% |
| Support share of financing base for support | 50.00% |
| Support share of total financing | 50.00% |
| Support share of other public co-financing | 50.00% |
| Support share of public co-financing | 100.00% |
| Support share of private co-financing | 0.00% |

Contacts

| Name: | Birger Winsa |
| --- | --- |
| Organisation: | Meänsuomen Föreeninki - Byfinska Föreningen |
| Phone: |  |
| Mobile phone: | +46739328330 |
| E-mail address: | birgerwinsa@yahoo.com |
| Role: | Contact person |
| Published in Projektbanken: |  |
| Name: | Kaarina Malinen |
| Organisation: | Runolaulu-Akatemian kannatusyhdistys ry |
| Phone: |  |
| Mobile phone: | +358443501394 |
| E-mail address: | kaarina.malinen@runolaulu.fi |
| Role: | Economy |
| Published in Projektbanken: |  |
| Name: | Marko Jouste |
| Organisation: | University of Oulu |
| Phone: |  |
| Mobile phone: | +358414363964 |
| E-mail address: | marko.jouste@oulu.fi |
| Role: | Contact person |
| Published in Projektbanken: |  |
| Name: | Pekka Huttu-Hiltunen |
| Organisation: | Runolaulu-Akatemian kannatusyhdistys ry |
| Phone: | +358401798600 |
| Mobile phone: | +358401798600 |
| E-mail address: | pekka.huttu-hiltunen@runolaulu.fi |
| Role: | Project leader |
| Published in Projektbanken: | Ja |
| Name: | Rune Bjerkli |
| Organisation: | Kvensk Finsk Riksforbund |
| Phone: |  |
| Mobile phone: | +4790144467 |
| E-mail address: | kvenfinn@gmail.com |
| Role: | Contact person |
| Published in Projektbanken: |  |

Documents